# TASC CONFERENCE COORDINATOR SCHOOL

# TIMELINE/CHECKLIST

Thank you for choosing to be a part of TASC history by coordinating the High School Annual Conference.  Your efforts and contributions are appreciated.

Please understand that this conference is a celebration of TASC.  The Conference Coordinator School has the opportunity to highlight its school and its talent.  However, this is a team effort.  No individuals, other than those who have earned awards or are designated for special recognition by TASC should be spotlighted as that is not the purpose of this conference.

Please know in advance that nothing is to take place on stage that has not been approved by the Production Company.  That company has been hired to manage production and entertainment, and we depend upon their professional judgment.  If there is a concern or difference of opinion, contact the TASC Director.

YEAR ONE:

- Shadow current coordinator school

- Consider taking video at conference to help with your fundraising efforts (to show what you will be doing and to use in your promo video)

- Fundraising plan

- Fundraising

- Secure key leaders

- Inform school board

- Begin building community support and funding

- Collaborate with State Officers between April and Steering Committee Retreat on theme ideas and logo

- Present at State Steering Committee Retreat & work with students/adults as theme and project are determined

- Present at summer board meeting

YEAR TWO:

SUMMER (AFTER BOARD MEETING)

- Begin to secure talent for show

- Design artwork for program cover

- Design artwork for t-shirt

- Collaborate with TASC Director on speakers for conference .(Director  wants your vision/input so speakers are appropriate)

- Have your support team in place

- Have concept for stage set, decorations, etc.

- Meet with representative from Production Company to generate set ideas

- Meet with officials at site to understand location/space, etc.

SEPTEMBER

- Present at Advisors Workshop

- Have  promo video ready

OCTOBER

- Meet in Arlington with TASC Director and production company

- Have opening GS ideas ready to discuss with production company

- Tour of site

- Meet with hotel and site representatives

- Check with TASC Director to ensure speakers are contracted

- Meet with convention visitors bureau representative

- Send artwork to TASC graphic artist for t-shirts, etc.  (logo)  (Recommend working with Herff Jones)

- Commitments from the following to create your team:

  - Students to attend

  - Parents to attend

  - Teacher volunteers (AV, Building Trades, etc.

NOVEMBER

- Present art design and update to TASC board

- Meet with officer team and review conference responsibilities while at the ML Conference

- Order student/advisor bags

- Reserve rooms at hotel

- Begin social media campaign to build interest (coordinate with state secretary)

- Contact housing bureau regarding rooms.

- Provide production company any additional ideas for opening GS

- Provide production company a list of any and all performance related groups/people available for the opening performance including number of performers broken down by gender. (Keep in mind that we are playing for nearly 5,000 people and need to have a BIG visual presentation

- Provide production company ideas and plan for any additional entertainment and/or presentation elements for other sessions of the conference (orchestras, bands, dancers, etc.)

- Provide production company an additional or new ideas for stage dressing and scenic look

- Have a general list of the running crew for the conference

DECEMBER

- Create decorations plan for site

- Create plan for advisor hospitality

JANUARY

- Have updated promotional video ready for TASC website

- Provide production company any music wanted to be played before/after each GS.  Provide sharable MP4 files on a thumb drive along with full lyrics for each song.  (Check carefully for appropriateness. Err on the side of caution.) 30 songs

- Order hospitality items from convention center (collaborate with TASC Director)

- Create food plan for your school

- Order staff t-shirts that are distinctive and recognizable

- Order conference bags (should have separate advisor bag)

- Arrange transportation

- Send videos of all production numbers to production company

- Meet with officer team and review conference responsibilities at Lakeview or Mo Ranch

- Send the following to TASC:

  - Superintendent’s photo for program

  - Superintendent’s welcome letter for program

  - Photo of advisor

  - Photo of principal

  - Photo of student representative

FEBRUARY

- Register 5 delegates and 1 advisor with TASC

- Order additional conference t-shirts for additional attendees

- At least 5 video clips to be used for conference inspiration to production company (Provide full HD Resolution UNCOMPRESSED files –edited and trimmed to the content desired.  These may be motivational or conference theme related clips from films, commercials, etc.  Check carefully for appropriateness.

- 15 inspirational quotes to be used in script to production company

- Anecdotes to production company

- DVD of opening and closing number to production company for critique

- Pictures of group, etc. to TASC for program

- Production company will want a list in order of all preshow entertainment along with videos

- Acknowledge that failure to meet Production Company guidelines may result in alternate sources for entertainment, changes in role of host school

- Gather items for advisor bags

- Gather door prizes for advisors

- Meet with officer team and review conference responsibilities at Lakeview or Mo Ranch

MARCH

- Superintendent’s speech to TASC Director

- Principal’s speech to TASC Director

- Student representative’s opening and closing speech to TASC Director

- Invocation to TASC Director with name of student giving nondenominational invocation/moment of inspiration

- Send names of students leading pledge, carrying TASC flag, and singing national anthem

- Begin providing videos of opening performances rehearsals on a weekly basis for any/all entertainment/enhancements.

- Send “Thank You” page list of sponsors for the program to TASC  (TASC needs all program information and script information no later than mid-March)

- Finalize hotel reservations (cancel extra rooms)

- Send TASC numbers for Six Flags Tickets, additional t-shirts, etc.   (Meet prereg deadline on shirt requests) Send this list in writing to TASC Program Assistant.

- Create job list for students and adults and send lists to TASC Director (facilitators, set up and strike crew, running crew, everyone available for rehearsals, registration crew

- Create transportation plan

- Create committee packets (for example: registration, production, sessions, general, etc.). Go over with students.

- Coordinate TASC and production company schedules. (“meeting” spreadsheet)

- Create awards and display for award winning schools

- Complete decorations/props for stage, etc.

- Receive name tags from TASC (If host is not counting shirts, bags could be stuffed onsite)

- Stuff student bags and box for transport (depending on location, may stuff bags in Arlington)

- Create packing list

- Organize materials to be taken

- Order additional Six Flags tickets (These can also be purchased onsite.)

- Review information about registration and facilitators (TASC director will send this.)

- Assign all students to specific teams. Assign facilitators to sessions, etc. Double check to see that your registration team and facilitators can meet per the TASC schedule.

ONE DAY BEFORE CONVENTION

ORGANIZE 3 TEAMS:  REGISTRATION, PRODUCTION, AND DECORATION

- Registration:  Count t-shirts (hopefully the shirt company will do this), fill advisor bags

- Production:  Load in, set up

- Decoration:  Set up site (foyer, hall way, hospitality room, etc.)

- Afternoon/evening:  practice opening number

- Observe closing time for site.  Failure to leave on time will incur overtime costs for CCS

DURING CONVENTION

- Check duties of host school

- Stay with schedule

- Provide conference highlight video featuring highlights from the conference weekend edited to appropriate music, 90- 150 seconds long.  This needs to be provided to production company the evening before the final session in full UNCOMPRESSED HD.  If you want to include Six Flags/Day two evening activities footage, have initial video to production company and discuss Six Flags/evening portion.

- Double check times of all meetings with TASC staff and production company. All members involved in meetings must be present

- Double check with production company regarding times crew is required for set up/break down, etc.  Failure to remain until site is cleared by Production Company will result in addition fees for host school.

FOLLOWING CONVENTION

- Pack

- Clean convention area

- Thank you notes

- Update/revise check list and notes for next host school and to TASC Director

- Provide follow up YouTube video for TASC website

- Send receipts to TASC for reimbursement

- Pay bills

- Celebrate your success